2018 GNSO Chair Election Timeline

|  |  |  |
| --- | --- | --- |
| Not Later Than: | Activity Commences | Time Available |
| Summer ICANN Meeting  27th June 2018 | Announce Proposed Procedure and Timeline | 1 day |
| T – 60 Days  25th August 2018 | NomCom Selectees Announced  SG/C New Council Members Announced  House Nominee Selection | 1 day  1 day  30 days |
| T – 30 days  24th September 2018 | Houses Submit Nominees | 1 day |
| T-18 Days  6th October 2018 | Candidates Submit Statements | 12 days |
| T-3 days  20 & 21 October 2018 | Candidate Meetings | 2 days |
| T  24 October 2018 | Election Held at Annual General Meeting | 1 day |
| T + 2 days  26 October 2018 | Council informs the Board and the Community and posts election results on the GNSO website | 2 days |