2018 GNSO Chair Election Timeline

|  |  |  |
| --- | --- | --- |
| Not Later Than: | Activity Commences | Time Available |
| Summer ICANN Meeting 27th June 2018 | Announce Proposed Procedure and Timeline  | 1 day  |
| T – 60 Days 25th August 2018 | NomCom Selectees Announced SG/C New Council Members Announced House Nominee Selection | 1 day 1 day30 days |
| T – 30 days24th September 2018 | Houses Submit Nominees | 1 day |
| T-18 Days6th October 2018 | Candidates Submit Statements  | 12 days |
| T-3 days20 & 21 October 2018 | Candidate Meetings | 2 days |
| T24 October 2018 | Election Held at Annual General Meeting  | 1 day |
| T + 2 days26 October 2018 | Council informs the Board and the Community and posts election results on the GNSO website | 2 days |